## Slide 1
Customer Success
Gen AI Programme
Programme Debrief for Diana
Presented by Azmain | March 2026
Moody's Analytics | Insurance Solutions

## Slide 2
Executive Overview
6
Workstreams
10
Projects
31
Scorecard
Accounts
11
Weeks
Running
Programme Mission
Accelerate AI adoption across Customer Success through practical tools, training, and prototyping
Six workstreams: enablement (WS1), core tooling (WS2), intelligent agents (WS3-WS4), automation (WS5), rapid innovation (WS6)
Reports into Natalia Orzechowska's organisation across multiple Insurance division teams
Diya Sawhny is executive sponsor
Priorities & Challenges
AMBER
CLARA adoption and data quality
Build in Five demo for May exceedance
Gainsight integration (hard launch March 30)
Salesforce one-way read via App Factory MCP
Cross-OU expansion (Banking, Life, AM interested)
Resource concentration risk (Azmain, BenVH, Richard)
AWS Bedrock costs on pace for $10K/month
Customer Success Gen AI Programme | Confidential
2

## Slide 3
Programme Landscape
All Projects at a Glance
WS2
CLARA
IRP Adoption Tracker — the primary tool
WS1
Training &
Enablement
AI upskilling & prompt engineering
WS3
CS Agent
Customer Success AI Agent
WS4
Friday
Internal PM app (Diana-sponsored)
WS5
Navigator L1
Automation
L1 support ticket automation
WS6
Build in Five
Rapid AI prototyping (Martin)
Cross OU
Collaboration
Banking, AM, Life Insurance outreach
Programme
Management
Governance, steering, portfolio
TSR
Enhancements
Cat bond TSR automation (Idris)
App Factory
BenVH's MCP server platform
Customer Success Gen AI Programme | Confidential
3

## Slide 4
CLARA
WS2 | IRP Adoption Tracker
LIVE
Overview
AMBER
CLARA tracks IRP adoption across customer success teams — the central tool CSMs use in weekly Portfolio Reviews facilitated by Natalia Orzechowska
31 scorecard migration accounts are the priority dataset
Live on AWS with CI/CD pipeline, RBAC, and two-week structured release cycle
Nikhil (50%) and Chris recently onboarded — Chris on bugs, Nikhil on scorecard tab
Priorities & Next Steps
GREEN
Gainsight integration alignment (hard launch March 30)
Salesforce one-way read — Cases + Case Feed via App Factory MCP
Scorecard tab and migration burndown completion
User Voice and HD model data integration
Challenges
AMBER
Data quality (not features) is the primary adoption challenge — CSMs still need hand-holding after four weeks
Azmain is single point of failure for features; BenVH is single point of failure for deployment
Scope creep from multiple new integration requirements
Customer Success Gen AI Programme | Confidential
4

## Slide 5
Build in Five
WS6 | Rapid AI Prototyping (Martin)
ON TRACK
Overview
GREEN
Framework for building demo apps on IRP's Risk Data Lake using Cursor during customer conversations
Martin built a near-complete dashboard builder that exceeded all expectations — drag-drop UI with data, visual, and AI modes
Full white-labelling: themes, dark mode, logos, branding, corner radius
Live Risk Modeller API connection already working — compared to Databricks Genie
Priorities & Next Steps
GREEN
Wire up Navigator MCP server — completes the live demo loop
Stakeholder cascade: tech consulting, then demo team, then sales, then exceedance
Target: May exceedance event (content due April)
Three-pronged convergence: Martin's dashboard + Nikhil's MCP + Elliot's profiling agent
Challenges
AMBER
Martin's 12-week assignment is time-limited — clock is ticking but output justifies investment
Product positioning unresolved: Moody's product feature vs customer self-service tool
AIG using MCP for underwriting — elevates this from demo tool to strategic engagement vehicle
Customer Success Gen AI Programme | Confidential
5

## Slide 6
App Factory
BenVH's MCP Server Platform
ON TRACK
Overview
GREEN
BenVH pivoting core to an MCP server — middleware that any app (CLARA, Slidey, Build in Five) can consume
Apps request an LLM worker, App Factory spins it up and returns the connection — apps stay simple
Connected to BenVH's patented Phantom Agent for enterprise AI governance
Asia-Pac interest (Singapore, Japan, Australia) adds validation and urgency
Priorities & Next Steps
GREEN
MCP server completion (targeting end of this week)
Martin's Build in Five as first integration proof of concept
Wednesday showcase with senior stakeholders and ISLTR in London
Inter-app communication: CLARA to Slidey via App Factory
Challenges
RED
BenVH is overloaded — MCP server, Slidey auth, Juliet's setup, Martin integration, all deployment duties
BenVH is the only deployer — acute burnout risk and single point of failure
No tested rollback procedure; schema changes have caused production breakage
Customer Success Gen AI Programme | Confidential
6

## Slide 7
Friday
WS4 | Internal PM App (Diana-sponsored)
IN PROGRESS
Overview
GREEN
Internal PM app like Monday.com, built by Azmain using 30 concurrent AI agents in one day
Features: Kanban, list/timeline views, milestones, budgeting, decision tracking, stakeholder heat maps
IRP projects sync bidirectionally with CLARA; non-IRP projects live only in Friday
Diana endorsed it to replace slide-based Wednesday advisory project review
Priorities & Next Steps
GREEN
Diana presenting Friday vision to Ben Brooks and Charlotte for formal approval
Deploy to dev (BenVH) without auth for a four-week pilot
Seed with Diana's Excel file as initial data
Prashant allocated to help with development
Challenges
AMBER
Adds to Azmain's already-stretched bandwidth across CLARA + five other workstreams
No formal budget or sanctioning yet — unclear if skunkworks or official
Cost concern: Azmain burned $500 Cursor budget in one day building it
Customer Success Gen AI Programme | Confidential
7

## Slide 8
Training & Enablement
WS1 | AI Upskilling Across Teams
STALLED
Overview
RED
Conceptual framework exists: solution-focused training buckets, competency assessment, train-the-trainer approach
No execution — CLARA consumed all of Azmain's bandwidth since January
Previous training session (Dec 2025): 40 attendees from 80 registered
Cross-OU enablement sessions delivered to Banking and Life (10 March)
Priorities & Next Steps
AMBER
Two grads arriving April 7 may provide execution capacity
Need an owner other than Azmain — or his workload must be redistributed
Share the insurance team's ROI approach and approval framework cross-OU
Challenges
RED
Remains stalled unless someone other than Azmain is allocated to execute
Framework is ready — resourcing is the sole blocker
Azmain flagged to Natalia O. as the biggest/quickest win but no time allocated
Customer Success Gen AI Programme | Confidential
8

## Slide 9
Customer Success Agent
WS3 | AI-Powered Customer Engagement
MINIMAL
Overview
RED
AI agent to support customer success interactions — augment CSM capabilities with AI-driven insights
Kevin Pern built a Copilot Studio + Salesforce prototype independently
No programme oversight or operational integration
Bernard (Life) built a separate Copilot health dashboard — parallel effort
Priorities & Next Steps
AMBER
Formal check-in with Kevin to assess what exists and what's needed
Potential alignment with Salesforce Cases integration (Kevin is one of four consumers)
Consider whether this converges with the broader Salesforce/App Factory strategy
Challenges
RED
Operating in isolation with no programme coordination
Risk of duplicate effort across Kevin's work, Bernard's dashboard, and the Salesforce integration
Azmain told Natalia O. this workstream needs engagement — no action taken yet
Customer Success Gen AI Programme | Confidential
9

## Slide 10
Navigator L1 Automation
WS5 | Support Ticket Automation
EARLY STAGE
Overview
AMBER
Concept: use Navigator's upcoming API support to auto-answer L1 support tickets
MCP server discussion held with product team (Cihan, Lonny) in February
No CS-side build started yet
Navigator MCP server is now Build in Five's top integration priority — potential synergy
Priorities & Next Steps
AMBER
Clarity on what CS needs to build vs what the product team delivers
MCP server integration with Martin's dashboard builder
Define CS requirements for L1 automation use cases
Challenges
AMBER
Lowest clarity of all workstreams — needs scoping before any resource commitment
Azmain admitted he doesn't fully understand the scope
Integration with existing ticketing systems requires coordination with product
Customer Success Gen AI Programme | Confidential
10

## Slide 11
Cross-OU Collaboration
Extending the Programme Across Moody's Divisions
EXPANDING
Overview
GREEN
Banking (Gina Greer, Olivier) and Life (Jack Cheyne, Christian Curran) both engaged via Diya-requested sessions
Both teams at the same stage insurance was in Nov 2025: siloed initiatives, no dedicated resources
Idrees Deen (banking) formally onboarded as first non-core team member — building retention dashboard
Template / flat-pack CLARA approach proposed for cross-OU reuse
Priorities & Next Steps
GREEN
Wednesday showcase meeting with ISLTR in London
Share ROI framework and approval approach cross-OU
Define resource model for cross-OU support (currently unfunded)
Challenges
AMBER
Every new team adds demand on BenVH (only deployer) and Azmain — expansion is unfunded
Each OU has different tools, processes, and maturity levels — one size won't fit all
Building trust and demonstrating value before asking for commitment
Customer Success Gen AI Programme | Confidential
11

## Slide 12
Programme Management
Governance, Steering & Portfolio Reviews
MATURING
Overview
AMBER
Diya endorsed three-pillar structure: IRP governance, customer intelligence, platform enablement
Catherine emerged as a governance ally — volunteered for App Factory intake decision tree
Formal Gainsight integration meeting set up with Tina Palumbo, Nadim, Rajesh
56 decisions logged, 44 risks tracked — meeting intelligence tracked systematically
Priorities & Next Steps
AMBER
Post-twelve-week business case still needs building (clock ticking)
App Factory governance approval board to be established
Formal documentation of contributions and credit attribution
Build Diana into the governance structure
Challenges
AMBER
Programme has scaled ambition without scaling governance
Post-twelve-week business case is unaddressed — Diya asked for outcomes and continuation plan
Meeting effectiveness varies — some meetings lack clear follow-through
Customer Success Gen AI Programme | Confidential
12

## Slide 13
TSR Enhancements
Cat Bond TSR Automation (Idris Abram)
IN PROGRESS
Overview
GREEN
Idris Abram formally onboarded with Ben Brooks's approval for dedicated time
Focus: automating TSR processes for cat bonds — first project outside core insurance CS team
First test of the programme's enablement model: take someone from another team, provide tooling, produce output
Idris has strong domain knowledge of cat bonds and TSRs
Priorities & Next Steps
GREEN
Define formal project scope and plan with Azmain's support
Manage politics with Arno (Idris's current line manager)
Build TSR automation as a reference implementation for enablement
Challenges
AMBER
Adds coordination overhead for Azmain — cat bond domain is new to the team
Need to demonstrate value quickly to justify Idris's reallocation of time
Overlap with Navigator L1 work requires careful delineation
Customer Success Gen AI Programme | Confidential
13

## Slide 14
Appendix
Detailed Programme Reference

## Slide 15
Key Stakeholders
Name | Role | Notes
Richard Dosoo | Programme / Operational Owner | Strategic bridge between vision and execution. Manages Diya relationship. Flight risk (interviewing NYC).
Azmain Hossain | PM & CLARA Developer | Builds everything. Reports to Diana. Stretched across CLARA, Friday, and 5 other workstreams.
Ben Brooks | Product Owner (de facto) | Built CLARA v1. Pushes for speed. Shopping CLARA cross-OU. Exceedance panel planning.
BenVH (Van Houten) | Infrastructure & Deployment | Only person who can deploy. App Factory architect. Owns patented Phantom Agent. Burnout risk.
Natalia Orzechowska | Senior Director / CS Lead | Runs Portfolio Reviews. Practical, process-focused. Your skip-level manager.
Natalia Plant | Gainsight Team Lead | Leads the Gainsight team. Key contact for Gainsight integration.
Martin Davies | Build in Five Developer | 12-week assignment. Output exceeds all expectations. Dashboard builder compared to Databricks Genie.
Nikhil | Tech Consulting (50/50) | Bedrock API working. Being redirected from App Factory due to interpersonal conflict with BenVH.
Chris M | Developer (CLARA) | Methodical, adapting well. Bug fixes. Next assignment: Salesforce integration.
Idrees Deen | Banking CS / Cross-OU | Cross-OU coalition builder. Retention dashboard. Strategic thinker, strong banking ally.
Idris Abram | TSR Enhancements | First expansion outside core team. Cat bond / TSR automation. Ben Brooks approved dedicated time.
Catherine | Data & Gainsight Governance | Strongest new ally. Volunteered for App Factory governance. Full advocate conversion.
Diya Sawhny | Executive Sponsor | Impatient with detail. Wants elevator pitches. Engagement improved after Feb governance session.
Full stakeholder map includes 40+ individuals across multiple teams and tiers.
Customer Success Gen AI Programme | Confidential
A1

## Slide 16
Key Milestones
Jan 6
Programme kick-off
Jan 14
First CLARA AWS deployment
Jan 21
Data input hub live; Portfolio Review designed
Jan 26
First live Portfolio Review; exec session with Ari/Diya
Feb 2
Data loss incident — trust damage with CSMs
Feb 12
CSM workshop hands-on sessions
Feb 23
Diya governance session; 3-pillar structure endorsed
Mar 3
Nikhil + Chris onboarded; Life SLT demo; Bedrock API working
Mar 4
Friday PM app revealed; 2-week release cycle adopted
Mar 10
Build in Five breakthrough; cross-OU sessions; Idris Abram onboarded
Mar 11
App Factory MCP pivot; Salesforce integration designed
Mar 30
Gainsight hard launch (upcoming)
May
Exceedance event — Build in Five demo target
Customer Success Gen AI Programme | Confidential
A2

## Slide 17
Top Risks & Watchlist
CRITICAL
Key personnel concentration
Richard (strategy), BenVH (infra), Azmain (features) carry the programme. Richard interviewing in NYC. BenVH emotionally depleted. No succession plan.
HIGH
AWS cost trajectory
Bedrock at $1,163 in two weeks, on pace for $10K/month. No per-project or per-user cost attribution. Tags not configured.
HIGH
Scope outpacing capacity
Salesforce, Gainsight, cross-OU, Asia-Pac all emerging simultaneously. Every new consumer adds load to a team that hasn't grown.
HIGH
Deployment fragility
No tested rollback procedure. BenVH is the only deployer. Schema changes have caused production breakage.
MEDIUM
Post-12-week business case
Diya asked for outcomes and a continuation plan. Not addressed. Clock is ticking.
MEDIUM
Gainsight March 30 launch
Hard date confirmed. Immediate questions about CLARA sync expected. Phase 2 planning needs to accelerate.
MEDIUM
Documentation debt
CLARA has zero formal documentation. If Azmain is unavailable, nobody can maintain it independently.
Customer Success Gen AI Programme | Confidential
A3

## Slide 18
Key Threads to Watch
CLARA Adoption
Are CSMs using it daily? Feedback loop functioning? Data quality blocking trust.
Resource Strain
Azmain's bandwidth, token costs, dev capacity across 10 projects. Grads arriving April.
Salesforce / Gainsight
Gainsight hard launch March 30. Salesforce one-way read designed. Both via App Factory MCP.
Build in Five Demo
Martin's May exceedance target. MCP server integration is the critical next step.
Cross-OU Expansion
Banking, AM, Life all interested. Wednesday showcase with ISLTR. Currently unfunded.
Stakeholder Engagement
Who's leaning in (Catherine, Idrees), who's drifting (Diya attention span).
BenVH / Nikhil Conflict
At breaking point. Richard planning confrontation. Nikhil to be redirected to Salesforce.
Governance Maturity
Transitioning from informal to structured. Post-12-week case needed. Catherine as new ally.
Customer Success Gen AI Programme | Confidential
A4