## Slide 1
CLARA-Gainsight
Integration Charter
Version 1.0 (Draft) | 13 March 2026
Author: Azmain Hossain
Customer Success Gen AI Programme
Moody's Analytics — Insurance Division

## Slide 2
1. Purpose
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026
2
This charter defines the scope, responsibilities, timeline, and success criteria for integrating CLARA with Gainsight.
It exists to ensure both teams have a shared understanding of what will be built, by whom, and by when — so that no party is surprised by requirements, resource demands, or delivery expectations during execution.
Scope
What data objects will be synchronised and in what order
Roles
Who owns what — Gainsight team vs CLARA team vs joint
Timeline
Phased milestones from charter sign-off through production
Criteria
Measurable success criteria for POC and production

## Slide 3
2. Background
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026
3
Gainsight
System of record for CSMs. Unified view of customer health, engagement, time tracking, and BAU activities. Production go-live: 30 March 2026.
CLARA
Cross-functional IRP adoption tracker. Serves CSMs, product, implementation, and advisory teams. Used in weekly Portfolio Reviews. Primary migration reporting surface.
The Problem
CSMs must duplicate data entry across both systems. Cross-functional teams lose visibility into CSM-side activities.
The Goal
Enable CSMs to work primarily in Gainsight while ensuring IRP adoption data flows seamlessly to CLARA, and cross-functional inputs in CLARA are visible back in Gainsight.

## Slide 4
3. Parties & Stakeholders
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026
4
CLARA Team
Name | Role
Azmain Hossain | Programme Manager & Lead Developer
Ben Brooks | Product Owner, CLARA
Richard Dosoo | Programme & Operational Owner
BenVH | Infrastructure Engineer (AWS, CI/CD, App Factory)
Gainsight / Business Systems Team
Name | Role
Tina Palumbo | Business Systems, Gainsight Programme Lead
Rajesh | Solution Architect, Gainsight
Shashank | Technical Lead, Gainsight Application
Nadeem | Project Manager, Gainsight Programme

## Slide 5
4. Guiding Principles
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026
5
1
Gainsight is the system of record for CSM BAU.
CSMs should not enter the same data in two systems.
2
CLARA is the system of record for cross-functional IRP tracking.
Product, implementation, and advisory teams work in CLARA.
3
Integration must be bi-directional.
Data flows both ways — CSM inputs and cross-functional inputs.
4
Neither system replaces the other.
Gainsight covers full lifecycle. CLARA covers IRP adoption.
5
Start small, prove connectivity, then expand.
POC must demonstrate end-to-end data flow first.
6
No disruption to active migrations.
2026 scorecard target (30+ migrations) takes priority.

## Slide 6
5. Scope — Phase Overview
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026
6
P1
Foundation
Accounts
(Parent + Sub)
Customer
Weekly Updates
P2
Core IRP Data
Contacts / Users
Blockers
(Bi-directional)
Success Criteria
P3
Extended Data
Product Adoption
Tasks / Activity
(Bi-directional)
Full Case Feed
P4+
Future Roadmap
MS 365 Context
Usage Telemetry
NPS Verbatim
GS Health Scores
▶
▶
▶

## Slide 7
5. Scope — Phase 1: Foundation
Accounts & Customer Updates
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026
7
Source Object | CLARA Target | Direction | Notes
Account (Parent + Sub) | parent_accounts / customers | GS → CLARA | Establishes account hierarchy. Must include parent-subsidiary relationships. CLARA currently holds 155+ active accounts.
Customer Weekly Updates | customer_updates | Bi-directional | Per-account executive summaries and meeting notes. CLARA auto-generates these from transcribed weekly calls. CSMs also enter updates in Gainsight. Both sources must be visible in both systems.

## Slide 8
5. Scope — Phase 2: Core IRP Data
Contacts, Blockers & Success Criteria
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026
8
Source Object | CLARA Target | Direction | Notes
Contact / User | employees (CSM assignments) | GS → CLARA | Maps CSMs and key contacts to accounts.
Case / Custom Object (Blocker) | blockers | Bi-directional | CSM-created blockers originate in Gainsight. Product/implementation-created blockers originate in CLARA. Both systems must reflect the full set.
Success Criteria (CSC) | success_criteria | Bi-directional | IRP use case success criteria tracked by CSMs in Gainsight, supplemented by product teams in CLARA.

## Slide 9
5. Scope — Phase 3: Extended Data
Adoption, Tasks & Case Feed
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026
9
Source Object | CLARA Target | Direction | Notes
Product Adoption (PAT) | product_adoption_ tracking | GS → CLARA | Adoption milestone data for IRP products.
Task / Activity | action_plans / items | Bi-directional | Cross-functional action items. CSM tasks from Gainsight, product/implementation tasks from CLARA.
Full Case Feed | case_feed (new table) | GS → CLARA | Historical case context for blocker analysis and reporting. New data object in CLARA.

## Slide 10
5. Scope — Phase 4+ Roadmap
Future state — requires separate scoping after Phases 1-3
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026
10
Capability | Description | Dependency
Microsoft 365 Context (Graph API) | Email + meeting signals per account to enrich CS Agent synthesis | Graph API access, security review
Usage Telemetry (MIDAS / Mixpanel) | Product usage signals for adoption scoring and proactive engagement | MIDAS integration, data pipeline
NPS Verbatim & Detractor CTAs | Survey data for sentiment overlay (closes AMBER scorecard item) | Qualtrics integration
Gainsight Health Scores (read-only) | CSM qualitative health as context signal — Gainsight remains SoR | Gainsight reporting API
Write-back to Salesforce / Gainsight | Gated, future-state capability — requires governance approval | Governance framework, security review

## Slide 11
6. Integration Architecture
Proposed pattern based on 12 March 2026 discussion
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026
11
Salesforce (CRM)
▼
Gainsight
CSM System of Record
Health | Engagement | Time Tracking
Use Cases | Blockers | Activities
CLARA
Cross-Functional IRP Tracker
Migration Reporting | Portfolio Reviews
Blockers | Adoption | Action Plans
▶
Batch (S3)
Accounts, Contacts
◀
▶
API (Real-time)
Blockers, Tasks, Updates
App Factory
Middleware
▲
Databricks
Reporting & Analytics
▼

## Slide 12
6. Integration Methods
Batch vs real-time by data type
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026
12
Data Type | Method | Frequency | Rationale
Account (Parent + Sub) | Batch (S3) | Daily | Low change frequency. Proven and low-risk.
Customer Weekly Updates | API (real-time) | On create/update | Auto-generated summaries from CLARA, CSM updates from Gainsight.
Contact / User | Batch (S3) | Daily | Low change frequency.
Blocker (Case / Custom) | API (real-time) | On create/update | CSMs and product teams need immediacy. Delay causes duplication.
Success Criteria | API (real-time) | On create/update | Active during engagements. Timeliness matters.
Product Adoption (PAT) | Batch (S3) | Daily | Milestone data, not time-critical.
Task / Activity | API (real-time) | On create/update | Cross-functional coordination requires immediacy.
Case Feed | Batch (S3) | Daily | Historical context. No real-time requirement.

## Slide 13
6. Authentication & Connectivity
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026
13
Gainsight Team Provides:
1. API documentation (endpoints, schemas, rate limits, error handling)
2. Authentication method and credentials (API key, OAuth, SSO — TBC)
3. S3 bucket configuration for batch exchange (IAM roles, encryption)
4. Sandbox / test environment access for POC
CLARA Team Provides:
1. CLARA API specification (REST endpoints for all in-scope objects)
2. Authentication details for CLARA's API
3. Data mapping document (GS field → CLARA field + transformations)
4. Test environment access
Middleware — App Factory
Integration orchestration managed through App Factory (CLARA's AWS infrastructure layer). Handles API orchestration, retry logic, data transformation, error logging, rate limiting, and backpressure management. This approach is vendor-agnostic — the integration layer can be adapted if underlying systems change.

## Slide 14
7. Responsibilities
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026
14
Gainsight Team Owns
• API documentation & access provisioning
• S3 bucket setup & batch export config
• Sandbox environment for POC
• Data export scheduling & reliability
• Webhook / event config for real-time sync
• Data model documentation
• CSM change management & training
• GS-side testing & validation
• Project management (Nadeem)
CLARA Team Owns
• API endpoints for receiving & sending data
• Data transformation & mapping logic
• Storage, indexing & display of GS data
• Integration orchestration (App Factory)
• CLARA-side testing & validation
• Reporting & dashboards
• Technical architecture & infrastructure
Joint Responsibilities
• Data mapping agreement
• Integration testing (end-to-end)
• Error handling & escalation procedures
• POC evaluation & go/no-go decision
• Ongoing monitoring & incident response

## Slide 15
8. Success Criteria — POC
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026
15
1
Connectivity proven
CLARA can authenticate with and read from the Gainsight API (or consume S3 exports).
2
Account sync working
At least 10 parent accounts with subsidiaries synced with correct hierarchy.
3
Blocker round-trip
A blocker created in either system appears in the other within 5 minutes.
4
Data integrity
Synced records match — no data loss, no field truncation, no encoding issues.
5
No regression
CLARA's existing functionality (Portfolio Reviews, dashboards, reporting) is unaffected.
6
Performance
API responses under 2 seconds. Batch jobs complete within agreed windows.

## Slide 16
8. Success Criteria — Production
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026
16
1
All Phase 1-3 data objects synchronised per the schedule defined in integration methods.
2
CSMs can enter IRP use cases and blockers in Gainsight and see them reflected in CLARA without manual intervention.
3
Cross-functional teams can enter blockers and action items in CLARA and have them visible in Gainsight without manual intervention.
4
Zero instances of CSMs needing to double-enter data across both systems for objects covered by the integration.
5
CLARA's management reporting accurately reflects data from both sources.
6
Integration uptime of 99.5% during business hours (08:00-18:00 GMT).

## Slide 17
9. Timeline — Constraints
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026
17
Gainsight Onboarding
30 March 2026 deadline (RMS, Cape, Predicate teams). No capacity for integration before this.
Post-Launch Stabilisation
~4 weeks after go-live (April 2026) for Gainsight to stabilise with new user groups.
CLARA Graduate Onboarding
Two rotating graduates arriving 7 April 2026. Available for integration support from May.
CLARA Team Priority
2026 insurance scorecard target (30+ migrations) is the primary obligation. Integration is secondary.

## Slide 18
9. Proposed Milestones
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026
18
Phase | Milestone | Target | Owner
0 | Charter signed off by both teams | TBD | Azmain / Tina
0 | Gainsight API documentation shared | TBD | Rajesh / Shashank
0 | CLARA API specification shared | TBD | Azmain / BenVH
0 | Data mapping document agreed | TBD | Joint
1 | POC environment setup (sandbox both sides) | TBD | Joint
1 | POC: Batch account sync + customer updates | TBD | Joint
1 | POC: Real-time blocker sync | TBD | Joint
1 | POC evaluation and go/no-go decision | TBD | Joint + Governance
2 | Phase 2 production build | TBD | Joint
3 | Phase 3 production build | TBD | Joint
4+ | Phase 4+ scoping begins | TBD | Joint

## Slide 19
9. Governance Checkpoints
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026
19
Integration work reviewed as part of CLARA governance (fortnightly Tuesday reviews, facilitated by Natalia Plant).
Gate 1
Charter Approval
Both teams and governance leads sign off on this charter.
Gate 2
POC Go / No-Go
Based on POC success criteria (Section 8). All six criteria must be met.
Gate 3
Phase 2 Go / No-Go
Based on POC results and resource availability.
Gate 4
Phase 3 Go / No-Go
Based on Phase 2 stability and remaining scope.
▶
▶
▶

## Slide 20
10. Risks & Mitigations
Risks 1-4
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026
20
HIGH
R1: Gainsight API limitations prevent real-time sync for blockers/tasks
Mitigation: POC specifically tests real-time capability. Fallback: near-real-time batch (every 15 min) via S3.
HIGH
R2: Integration work diverts CLARA team from migration support
Mitigation: Integration is explicitly secondary. Governed via fortnightly reviews. Graduates (from May) allocated to integration.
MEDIUM
R3: Data model mismatch between Gainsight and CLARA
Mitigation: Data mapping agreed before build. Transformation centralised in App Factory middleware.
MEDIUM
R4: Gainsight team capacity constrained by RMS onboarding
Mitigation: Timeline accounts for March-April stabilisation. No POC work until May at earliest.

## Slide 21
10. Risks & Mitigations
Risks 5-8
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026
21
MEDIUM
R5: Bi-directional sync creates data conflicts
Mitigation: Clear ownership rules per data type. Conflict resolution: source system wins. Audit trail for all sync ops.
MEDIUM
R6: Scope creep into Phase 4+ items during POC
Mitigation: Phase 4+ explicitly deferred. Any additions require governance approval and charter amendment.
MEDIUM
R7: CSM adoption of new Gainsight IRP workflows is low
Mitigation: Gainsight team owns CSM change management and training. CLARA provides cross-functional docs.
LOW
R8: Authentication/security review delays access provisioning
Mitigation: Raise security review requests early (Phase 0). Both teams engage security contacts in parallel.

## Slide 22
11. Change Control
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026
22
Any changes to scope, timeline, or responsibilities must follow this process:
1
Raised in writing (email or shared document comment)
|
2
Reviewed at the next fortnightly governance session
|
3
Agreed by both CLARA lead (Azmain) and Gainsight lead (Tina)
|
4
Approved by governance (Natalia Orzechowska)
|
5
Documented as a charter amendment with version number and date
No work outside the defined scope will be undertaken without an approved charter amendment.

## Slide 23
12. Assumptions
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026
23
1
Gainsight will have stable API and S3 export capabilities available for the POC.
2
The Gainsight team will provide dedicated technical resource (Rajesh/Shashank) for integration sessions.
3
CLARA's existing AWS infrastructure (App Factory) can support the integration middleware without additional provisioning.
4
Both teams will have sandbox/test environments available that mirror production data structures.
5
CSMs will have been trained on entering IRP data in Gainsight before the integration goes live.
6
Salesforce data (accounts, contacts, cases) will continue to flow into Gainsight and does not need to be independently sourced by CLARA.

## Slide 24
Next Steps
1. Review and agree this charter (both teams)
2. Exchange API documentation and specifications
3. Agree data mapping document
4. Schedule POC kick-off (post Gainsight stabilisation)
CLARA-Gainsight Integration Charter | v1.0 Draft | 13 March 2026