## Slide 1
Customer Success
Gen AI Programme
Debrief for Diana
March 2026

## Slide 2
Programme at a Glance
10
Active
Projects
31
Scorecard
Accounts
56
Decisions
Logged
11
Weeks
Running
Priorities
Stabilise CLARA and deepen CSM adoption via weekly Portfolio Reviews
Land the Build in Five demo at May exceedance event
Integrate with Gainsight (launching March 30) and Salesforce
Scale App Factory as a shared MCP middleware for all AI apps
Expand cross-OU (Banking, Life, Asset Management interested)
Key Challenges
Resource concentration: Azmain, BenVH, and Richard carry nearly everything
Scope expanding faster than capacity (Salesforce, Gainsight, cross-OU, Asia-Pac)
AWS Bedrock costs on pace for $10K/month with no attribution
Deployment depends on a single person (BenVH) with no tested rollback
Post-twelve-week business case still unaddressed
2 / 16
Customer Success Gen AI Programme

## Slide 3
CLARA (IRP Adoption Tracker)
LIVE — Stabilising
Lead: Azmain (dev) · Ben Brooks (product) · BenVH (infra)
Current State
Live on AWS, used in weekly Portfolio Reviews facilitated by Natalia Orzechowska
31 scorecard migration accounts tracked as priority dataset
Nikhil (50%) and Chris onboarded — Chris on bugs, Nikhil on scorecard tab
Two-week structured release cycle adopted (replaces ad-hoc deploys)
Bedrock API key working; RBAC implemented
Data quality (not features) is the primary adoption challenge
Template / flat-pack approach proposed for cross-OU reuse
Next Steps
Gainsight integration alignment (hard launch March 30)
Salesforce one-way read (Cases + Case Feed via App Factory MCP)
Scorecard tab and migration burndown completion
User Voice and HD model data integration
Key Risk: Azmain is the single point of failure for features. BenVH is the single point of failure for deployment. Both are under significant pressure.
3 / 16
Customer Success Gen AI Programme

## Slide 4
Build in Five
ACTIVE — Breakthrough
Lead: Martin Davies · Richard (vision)
Current State
Martin built a near-complete dashboard builder that exceeded all expectations
Drag-drop UI with data, visual, and custom AI modes per component
Full white-labelling: themes, dark mode, logos, branding, corner radius
Live Risk Modeller API connection already working
Richard compared it to Databricks Genie — a capability the product team has but won't show
AIG intelligence: strategic deals with Anthropic and Palantir elevate this from demo tool to strategic engagement vehicle
Next Steps
Wire up Navigator MCP server — completes the live demo loop
Stakeholder cascade: tech consulting, then demo team, then sales, then exceedance
Target: May exceedance event (content due April)
Elliot's blueprint profiling agent as the third convergence piece
Key Risk: Martin's 12-week assignment is time-limited. Product positioning unresolved — Moody's product feature vs customer self-service tool.
4 / 16
Customer Success Gen AI Programme

## Slide 5
App Factory
ACTIVE — MCP Pivot
Lead: BenVH
Current State
BenVH pivoting core to an MCP server — middleware that any app can consume
Apps request an LLM worker, App Factory spins it up and returns the connection
Eliminates standalone UI — makes platform portable and composable
Connected to BenVH's patented Phantom Agent for AI governance
Asia-Pac interest (Singapore, Japan, Australia) adds validation and urgency
28 applications already linked to the platform
Next Steps
MCP server completion (targeting end of this week)
Martin's Build in Five as first integration proof of concept
Wednesday showcase meeting with senior stakeholders and ISLTR
Inter-app communication: CLARA to Slidey via App Factory
Key Risk: BenVH is overloaded — MCP server, Slidey auth, Juliet walkthrough, Martin integration, all existing deployment duties. Burnout risk is acute.
5 / 16
Customer Success Gen AI Programme

## Slide 6
Friday (PM App)
ACTIVE — Diana-sponsored
Lead: Azmain (dev) · Diana (sponsor)
Current State
Internal PM app like Monday.com, built by Azmain using 30 concurrent AI agents in one day
Features: Kanban, list/timeline views, milestones, budgeting, decision tracking, stakeholder heat maps
IRP projects sync bidirectionally with CLARA; non-IRP projects live only in Friday
Diana endorsed it to replace slide-based Wednesday advisory project review
Prashant allocated to help with development
Next Steps
Diana presenting Friday vision to Ben Brooks and Charlotte for formal approval
Deploy to dev (BenVH) without auth for a four-week pilot
Seed with Diana's Excel file as initial data
Key Risk: Adds to Azmain's already-stretched bandwidth. No formal budget or sanctioning yet — unclear if skunkworks or official.
6 / 16
Customer Success Gen AI Programme

## Slide 7
Training & Enablement
STALLED
Lead: Azmain (nominal) · Pietro, Stephanie, Colin (advisory)
Current State
Conceptual framework exists: solution-focused training buckets, competency assessment, train-the-trainer
No execution — CLARA consumed all of Azmain's bandwidth
Previous training session (Dec 2025): 40 attendees from 80 registered
Azmain flagged to Natalia O. as the biggest/quickest win but no time allocated
Cross-OU enablement sessions delivered to Banking and Life (10 March)
Next Steps
Two grads arriving April 7 may provide execution capacity
Need an owner other than Azmain — or his workload must be redistributed
Share the insurance team's ROI approach and approval framework cross-OU
Key Risk: Remains stalled unless someone other than Azmain is allocated to execute. Framework is ready — resourcing is the blocker.
7 / 16
Customer Success Gen AI Programme

## Slide 8
Customer Success Agent
MINIMAL PROGRESS
Lead: Kevin Pern
Current State
Kevin built a Copilot Studio + Salesforce prototype independently
No programme oversight or operational integration
Being partially addressed through Salesforce integration alignment
Bernard (Life) built a separate Copilot health dashboard
Azmain told Natalia O. this workstream needs engagement
Next Steps
Formal check-in with Kevin to assess what exists and what's needed
Potential alignment with Salesforce Cases integration (Kevin is one of four consumers)
Consider whether this converges with the broader Salesforce/App Factory strategy
Key Risk: Operating in isolation. Risk of duplicate effort without programme coordination.
8 / 16
Customer Success Gen AI Programme

## Slide 9
Navigator L1 Automation
EARLY STAGE
Lead: Product team (Cihan, Lonny)
Current State
Concept: use Navigator's upcoming API support to auto-answer L1 tickets
MCP server discussion held with Cihan and Lonny (19 Feb)
No CS-side build started yet
Azmain admitted he doesn't fully understand it
Navigator MCP server is now Build in Five's top integration priority
Next Steps
Clarity on what CS needs to build vs what the product team delivers
MCP server integration with Martin's dashboard builder
Define CS requirements for L1 automation use cases
Key Risk: Lowest clarity of all workstreams. Needs scoping before any resource commitment.
9 / 16
Customer Success Gen AI Programme

## Slide 10
Cross-OU Collaboration
EXPANDING
Lead: Richard · Idrees (banking ally)
Current State
Banking (Gina Greer, Olivier) and Life (Jack Cheyne, Christian Curran) both engaged via Diya-requested sessions
Both teams at the same stage insurance was in Nov 2025: siloed initiatives, no dedicated resources
Idrees Deen (banking) formally onboarded as first non-core team member — working on retention dashboard
Template / flat-pack CLARA approach proposed for cross-OU reuse
Wednesday showcase meeting planned with ISLTR in London
Next Steps
Share ROI framework and approval approach cross-OU
Wednesday meeting with insurance, banking, asset management
Define resource model for cross-OU support (currently unfunded)
Key Risk: Every new team adds demand on BenVH (the only deployer) and Azmain. Expansion is unfunded.
10 / 16
Customer Success Gen AI Programme

## Slide 11
Programme Management
ACTIVE — Maturing
Lead: Richard · Azmain
Current State
Diya endorsed three-pillar structure: IRP governance, customer intelligence, platform enablement
Catherine emerged as a governance ally — volunteered for App Factory intake decision tree
Formal Gainsight integration meeting set up with new stakeholders (Tina Palumbo, Nadim, Rajesh)
56 decisions logged, 44 risks tracked, 9 analytical trackers maintained
Meeting intelligence tracked systematically across all programme conversations
Next Steps
Post-twelve-week business case still needs building
App Factory governance approval board to be established
Formal documentation of contributions and credit attribution
Key Risk: Post-twelve-week business case is unaddressed and the clock is ticking. Programme has scaled ambition without scaling governance.
11 / 16
Customer Success Gen AI Programme

## Slide 12
TSR Enhancements
ACTIVE — New
Lead: Idris Abram · Azmain (support)
Current State
Idris Abram formally onboarded with Ben Brooks's approval for dedicated time
Focus: TSR automation for cat bonds — first project outside core insurance CS team
First test of the programme's enablement model: take someone from another team, provide tooling, produce output
Idris operating at a strategic level with strong domain knowledge of cat bonds and TSRs
Next Steps
Define formal project scope and plan with Azmain's support
Manage politics with Arno (Idris's current line manager)
Build TSR automation as a reference implementation for enablement
Key Risk: Adds coordination overhead for Azmain. Cat bond domain is unfamiliar to the team. Manageable if contained.
12 / 16
Customer Success Gen AI Programme

## Slide 13
Appendix
Detailed reference material
13 / 16
Customer Success Gen AI Programme

## Slide 14
Key People
Name | Role | Notes
Richard Dosoo | Programme / Operational Owner | Strategic bridge between vision and execution. Manages Diya relationship. Flight risk (interviewing NYC).
Azmain Hossain | PM & CLARA Developer | Builds everything. Reports to Diana. Stretched across CLARA, Friday, and 5 other workstreams.
Ben Brooks | Product Owner (de facto) | Built CLARA v1. Pushes for speed. Shopping CLARA cross-OU. Exceedance panel planning.
BenVH (Van Houten) | Infrastructure & Deployment | Only person who can deploy. App Factory architect. Owns patented Phantom Agent. Burnout risk.
Natalia Orzechowska | Senior Director / CS Lead | Runs Portfolio Reviews. Practical, process-focused. Your skip-level manager.
Natalia Plant | Gainsight Team Lead | Leads the Gainsight team. Key contact for Gainsight integration.
Martin Davies | Build in Five Developer | 12-week assignment. Output exceeds expectations. Dashboard builder compared to Databricks Genie.
Nikhil | Tech Consulting (50% AF / 50% CLARA) | Bedrock API working. Being redirected from App Factory due to interpersonal conflict.
Chris M | Developer (CLARA bugs) | Methodical, adapting well. Next assignment: Salesforce integration.
Idrees Deen | Banking CS / Cross-OU | Cross-OU coalition builder. Retention dashboard. Strategic thinker, strong banking ally.
Idris Abram | TSR Enhancements | First expansion outside core team. Cat bond / TSR automation. Ben Brooks approved dedicated time.
Catherine | Data & Gainsight Governance | Strongest new ally. Volunteered for App Factory governance. Full advocate conversion.
Diya Sawhny | Executive Sponsor | Impatient with detail. Wants elevator pitches. Engagement improved after Feb governance session.
14 / 16
Customer Success Gen AI Programme

## Slide 15
Key Milestones
Jan 6
Programme kick-off
Jan 14
First CLARA AWS deployment
Jan 21
Data input hub live; Portfolio Review designed
Jan 26
First live Portfolio Review; exec session with Ari/Diya
Feb 2
Data loss incident — trust damage
Feb 12
CSM workshop hands-on sessions
Feb 23
Diya governance session; 3-pillar structure endorsed
Mar 3
Nikhil + Chris onboarded; Life SLT demo; Bedrock API working
Mar 4
Friday PM app revealed; 2-week release cycle adopted
Mar 10
Build in Five breakthrough; cross-OU sessions; Idris Abram onboarded
Mar 11
App Factory MCP pivot; Salesforce integration designed
Mar 30
Gainsight hard launch (upcoming)
May
Exceedance event — Build in Five demo target
15 / 16
Customer Success Gen AI Programme

## Slide 16
Top Risks & Watchlist
CRITICAL
Key personnel concentration
Richard (strategy), BenVH (infra), Azmain (features) carry the programme. Richard interviewing in NYC. BenVH emotionally depleted. No tested succession plan.
HIGH
AWS cost trajectory
Bedrock at $1,163 in two weeks, on pace for $10K/month. No per-project or per-user cost attribution. Tags not configured.
HIGH
Scope outpacing capacity
Salesforce, Gainsight, cross-OU, Asia-Pac all emerging simultaneously. Every new consumer adds load to a team that hasn't grown.
HIGH
Deployment fragility
No tested rollback procedure. BenVH is the only deployer. Schema changes have caused production breakage.
MEDIUM
Post-12-week business case
Diya asked for outcomes and a continuation plan. This has not been addressed. Clock is ticking.
MEDIUM
Gainsight March 30 launch
Hard date confirmed. Immediate questions about CLARA sync expected. Phase 2 planning needs to accelerate.
MEDIUM
Documentation debt
CLARA has zero formal documentation. If Azmain is unavailable, nobody can maintain it independently.
16 / 16
Customer Success Gen AI Programme